## EXAMPLE - Agile Project Pla REA
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | Searching open-license media |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | Phuong Truong |  |  | 2025-02-12 | 23/4 | 0% | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
No | SPRINT 1 |  | Phuong Truong |  | 2025-02-12 | 2025-02-25 | 14
Yes | Feature 1 | Build code base and service related | Phuong Truong |  | 2025-02-12 | 2025-02-17 | 6 | Complete
No | Feature 2 | User management with Oauth secure | Phuong Truong |  | 2025-02-20 | 2025-02-25 | 6 | Complete
No | Feature 3 | Documentation chapter 1 | Phuong Truong |  | 2025-02-12 | 2025-02-25 | 14 | Complete
No | SPRINT 2 |  | Phuong Truong |  | 2025-02-26 | 2025-03-11 | 14
No | Feature 4 | Integration with Openverse API | Phuong Truong |  | 2025-02-26 | 2025-03-11 | 14 | Complete
Yes | Feature 5 | Documentation chapter 2 | Phuong Truong |  | 2025-02-26 | 2025-03-11 | 14 | Complete
No | SPRINT 3 |  | Phuong Truong |  | 2025-02-26 | 2025-03-25 | 28
No | Feature 6 | Documentation chapter 3 | Phuong Truong |  | 2025-02-26 | 2025-03-11 | 14 | Complete
No | Feature 7 | Registration and login page interface | Phuong Truong |  | 2025-03-12 | 2025-03-25 | 14 | Complete
No | Feature 8 | Homepage interface | Phuong Truong |  | 2025-03-12 | 2025-03-25 | 14 | Complete
No | Feature 9 | Searching interface | Phuong Truong |  | 2025-03-12 | 2025-03-25 | 14 | Complete
No | Feature 10 | Media interface | Phuong Truong |  | 2025-03-12 | 2025-03-25 | 14 | Complete
No | SPRINT 4 |  | Phuong Truong |  | 2025-03-26 | 2025-04-07 | 13
| Feature 11 | Build automated testing stategy | Phuong Truong |  | 2025-03-26 | 2025-04-07 | 13 | Complete
| Feature 12 | Add automated building stategy | Phuong Truong |  | 2025-03-26 | 2025-04-07 | 13 | Complete
| Feature 13 | Documentation chapter 4 | Phuong Truong |  | 2025-03-26 | 2025-04-07 | 13 | Complete
No | SPRINT 5 |  | Phuong Truong |  | 2025-04-08 | 2025-04-23 | 16
| Feature 13 | Documentation chapter 5 and final check | Phuong Truong |  | 2025-04-08 | 2025-04-23 | 16 | Complete
Formulas:
START DATE = MIN([START DATE, row below]:G9)
END DATE = MAX([END DATE, row below]:H9)
END DATE = MAX([END DATE, row below])

## EXAMPLE - Agile Project Plan (hidden)
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | Searching open-license media |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | Phuong Truong |  |  | 2025-02-12 | 2025-10-10 | 0% | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
No | SPRINT 1 |  | Phuong Truong |  | 2025-02-12 | 2025-02-25 | 14
Yes | Feature 1 | User management with Oauth secure | Phuong Truong |  | 2025-02-12 | 2025-02-25 | 14 | Complete
No | Feature 2 |  | Phuong Truong |  | 2025-02-12 | 2025-02-25 | 14 | In Progress
No | Feature 3 |  | Phuong Truong |  | 2025-02-12 | 2025-02-25 | 14 | Overdue
No | SPRINT 2 |  | Phuong Truong |  | 2025-02-26 | 2025-03-11 | 14
No | Feature 4 | Registration and login page interface | Phuong Truong |  | 2025-02-26 | 2025-03-11 | 14 | Approved
Yes | Feature 5 | Homepage interface | Phuong Truong |  | 2025-02-26 | 2025-03-11 | 14 | Needs Review
No | Feature 6 |  | Phuong Truong |  | 2025-02-26 | 2025-03-11 | 14 | On Hold
No | SPRINT 3 |  | Phuong Truong |  | 2025-03-12 | 2025-10-05 | 208
No | Feature 7 |  | Phuong Truong |  | 2025-03-12 | 2025-03-25 | 14 | Not Started
No | Feature 8 |  | Phuong Truong |  | 2025-03-12 | 2025-10-02 | 205 | Not Started
No | Feature 9 |  | Phuong Truong |  | 2025-03-12 | 2025-10-05 | 208 | Not Started
Formulas:
START DATE = MIN([START DATE, row below]:G9)
END DATE = MAX([END DATE, row below]:H9)

## BLANK - Agile Project Plan (hidden)
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME |  |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | [6 empty] | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
| SPRINT 1 |  |  |  | 0 | 0
Feature 1
Feature 2
Feature 3
| SPRINT 2 |  |  |  | 0 | 0
Feature 4
Feature 5
Feature 6
| SPRINT 3 |  |  |  | 0 | 0
Feature 7
Feature 8
Feature 9
Formulas:
START DATE = MIN([START DATE, row below]:G9)
END DATE = MAX([END DATE, row below]:H9)
Double click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Dropdown Keys - Do Not Delete - (hidden)
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold